## Gantt Chart
Project proposal title: | Tailoring light-matter interaction: from topological and quantum phenomena to new functional materials
Acronym: | LIGHTMat
Principal Investigator (PI): | dr Aleksandra Maluckov
Description Months | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Work Package 1
Subactivity 1.1.1
Subactivity 1.1.2
Subactivity 1.1.3
Subactivity 1.2
Work Package 2
Subactivity 2.1.1
Subactivity 2.1.2
Subactivity 2.2.1
Subactivity 2.2.2
Subactivity 2.2.3
Subactivity 2.3.1
Subactivity 2.3.2
Work Package 3
Subactivity 3.1.1
Subactivity 3.1.2
Subactivity 3.1.3
Subactivity 3.2
Subactivity 3.3.1
Subactivity 3.3.2
Subactivity 3.4
Work Package 4
Subactivity 4.1.1
Subactivity 4.1.2
Subactivity 4.2.1
Subactivity 4.2.2
Work Package 5
Activity 5.1
Activity 5.2
Activity 5.3
Activity 5.4
Milestones and Deliverables
Milestone and Deliverables 1.1.1 | [8 empty] | MS |  |  | DL | [5 empty] | DL | [5 empty] | DL |  | DL
Milestone and Deliverables 1.1.2 | [23 empty] | MS | [11 empty] | DL
Milestone and Deliverables 1.1.3 | [9 empty] | MS | [9 empty] | DL
Milestone and Deliverables 1.2 | [24 empty] | MS | [5 empty] | DL
Milestone and Deliverable 2.1.1 | [5 empty] | MS | [7 empty] | DL
Milestone and Deliverable 2.1.2 | [34 empty] | DL
Milestone and Deliverable 2.2.1 | [8 empty] | MS |  |  |  | DL
Milestone and Deliverable 2.2.2 | [18 empty] | MS |  |  |  | DL
Milestone and Deliverables 2.2.3 | [21 empty] | DL | [10 empty] | DL
Milestone and Deliverables 2.3.1 | [12 empty] | DL
Milestone and Deliverables 2.3.2 | [21 empty] | MS | [12 empty] | DL
Milestone and Deliverables 3.1.1 | [11 empty] | DL
Milestone and Deliverables 3.1.2 | [11 empty] | MS | [11 empty] | DL
Milestone and Deliverables 3.1.3 | [35 empty] | DL
Milestone and Deliverables 3.2 | [17 empty] | MS | [5 empty] | DL
Milestone and Deliverables 3.3.1 | [17 empty] | DL
Milestone and Deliverables 3.3.2 | [23 empty] | MS |  | DL
Milestone and Deliverables 3.4 | [35 empty] | DL
Milestone and Deliverable 4.1.1 | [5 empty] | MS |  |  |  |  | DL
Milestone and Deliverable 4.1.2 | [17 empty] | MS | [5 empty] | DL
Milestone and Deliverables 4.2.1 | [23 empty] | MS |  | DL
Milestone and Deliverables 4.2.2 | [35 empty] | DL
Deliverable 5.1. | [5 empty] | DL
Deliverable 5.2 | DL | [19 empty] | DL
Deliverable 5.3 | [11 empty] | DL | [22 empty] | DL
Deliverable 5.4 | [5 empty] | DL | [5 empty] | DL | [5 empty] | DL | [5 empty] | DL | [5 empty] | DL | [5 empty] | DL
Deliverable 5.5 | [26 empty] | DL
Deliverable 5.6 (naknadno)
Participants (% of working time)* | [36 empty] | Effective person-months
Principal investigator (PI) | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 10.8
Participant 1 (P1) | 25 | 25 | 25 | 25 | 30 | 30 | 30 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 30 | 30 | 30 | 30 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 20 | 10 | 10 | 9
Participant 2 (P2) | 15 | 25 | 25 | 25 | 25 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 25 | 25 | 25 | 25 | 20 | 15 | 15 | 15 | 15 | 15 | 10 | 10 | 9
Participant 3 (P3) | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 10.8
Participant 4 (P4) | 25 | 25 | 25 | 25 | 30 | 30 | 30 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 30 | 30 | 30 | 30 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 20 | 10 | 10 | 9
Participant 5 (P5) | 10 | 10 | 10 | 10 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 7.2
Participant 6 (P6) | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 10.8
Participant 7 (P7) | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 10.8
Participant 8 (P8) | 10 | 10 | 10 | 10 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 20 | 25 | 25 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 7.2
Participant 9 (P9) | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 9
Participant 10 (P10) | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 10.8
Participant 11 (P11) | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 10.8
Total effective person-months
*In case that the project proposal involve participant from Diaspora and/or retired university professor/retired principal research fellow/professor emeritus/retired member of the Serbian Academy of Sciences and Arts please note that this participant should be presented in the Gantt Chart in all segments as other participants, including % of working time dedicated to the project.